## Sheet1
Jones Family Solar Power Project Parts List
2020-11-29
[6 empty] | quantity |  |  |  | cost
Item no. | Description | Make | Model | Supplier | unit price | phase 1 | phase 2 | phase 3 | total | phase 1 | phase 2 | phase 3 | total | ordered? | procured? | notes
1 | 180W 60 cell solar panel | Sharp | NT-180U1 | n/a | 0 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | n/a | yes | in service since 2003
2 | 360W 60 cell solar panel | LG | LG360N1C-N5 | Unbound Solar | 418 | 0 | 9 | 9 | 18 | 0 | 3762 | 3762 | 7524
3 | standing seam metal roof clamp used | S5! | S5-U | n/a | 0 | 48 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  |  | in service since 2007
4 | standing seam metal roof clamp new | S5! | S5-U | Unbound Solar | 13 | 0 | 36 | 36 | 72 | 0 | 468 | 468 | 936
5 | solar panel hold-down clamp used |  |  | n/a | 0 | 48 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  |  | in service since 2007
6 | solar panel hold-down clamp new |  |  | Unbound Solar | 3 | 0 | 36 | 36 | 72 | 0 | 108 | 108 | 216 |  |  | price of L-foot; not sure what is needed for LG
7 | 6 position combiner box | Midnite Solar | MNPV6 | Unbound Solar | 115 | 2 | 0 | 0 | 2 | 230 | 0 | 0 | 230
8 | 3 position combiner box | Midnite Solar | MNPV3 | Unbound Solar | 90 | 0 | 1 | 1 | 2 | 0 | 90 | 90 | 180
9 | main input breaker panel 24 position |  |  | n/a | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | n/a | yes | in service since before 2001
10 | critical loads breaker panel 24 position |  |  | Home Depot |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
11 | Breaker DC DIN 10A 150V 13mm | Midnite Solar | MNEPV-10 | Unbound Solar | 15 | 4 | 0 | 0 | 4 | 60 | 0 | 0 | 60
12 | Breaker DC DIN 15A 150V 13mm | Midnite Solar | MNEPV-15 | Unbound Solar | 15 | 0 | 3 | 3 | 6 | 0 | 45 | 45 | 90
13 | Breaker DC DIN 50A 150V 13mm | Midnite Solar | MNEPV-50 | Unbound Solar | 15 | 1 | 0 | 0 | 1 | 15 | 0 | 0 | 15
14 | Breaker DC DIN 80A 150V 26mm | Midnite Solar | MNEPV-80 | Unbound Solar | 44 | 0 | 1 | 1 | 2 | 0 | 44 | 44 | 88 |  |  | MNEPV-100 price; call for 80A price
15 | Breaker DC 250A 125V 3/8" studs 1.5" wide | Midnite Solar | MNEDC-250 | Unbound Solar | 95 | 1 | 1 | 1 | 3 | 95 | 95 | 95 | 285
16 | Breaker AC DIN 40A 240V 2-pole 26mm | Midnite Solar | MNEAC40-2P | Unbound Solar | 29 | 5 | 0 | 0 | 5 | 145 | 0 | 0 | 145
17 | 3 position insulated bus bar |  |  | Unbound Solar |  | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0
18 | 4 position insulated bus bar |  |  | Unbound Solar |  | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0
19 | 5 position insulated bus bar |  |  | Unbound Solar |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
20 | 7 position insulated bus bar |  |  | Unbound Solar |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
21 | 3 position bus bar |  |  | Unbound Solar |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
22 | 4 position bus bar |  |  | Unbound Solar |  | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0
23 | 5 position bus bar |  |  | Unbound Solar |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
24 | 7 position bus bar |  |  | Unbound Solar |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
25 | charge controller 150VDC in 80A 80V out | Outback Power | FlexMax FM80 | Unbound Solar | 515 | 1 | 1 | 1 | 3 | 515 | 515 | 515 | 1545
26 | inverter/charger 48VDC in 240V 8kW out | Outback Power | GS8048-01 | Unbound Solar | 4295 | 1 | 0 | 0 | 1 | 4295 | 0 | 0 | 4295
27 | inverter/charger remote | Outback Power | Mate3s | Unbound Solar | 437 | 1 | 0 | 0 | 1 | 437 | 0 | 0 | 437
28 | communication manager | Outback Power | Hub-10 | Unbound Solar | 225 | 1 | 0 | 0 | 1 | 225 | 0 | 0 | 225
29 | RJ-11 cable |  |  |  |  | 2 | 1 | 1 | 4 | 0 | 0 | 0 | 0
30 | mechanical interlock |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
31 | UPS |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
32 | system control box | homemade |  | n/a |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | expand list to show subcomponents
33 | battery box | homemade |  | n/a |  | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 0 |  |  | expand list to show subcomponents
34 | system control PCA | homemade |  | n/a |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | expand list to show subcomponents
35 | 48V LiFePO4 BMS PCA | homemade |  | n/a |  | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 0 |  |  | expand list to show subcomponents
36 | temp sensor |  |  |  |  | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 0
37 | Hall effect current sensor 625A .69" gap used | Honeywell | CSLA1EL | n/a | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | n/a | yes | leftover from EV conversion project
38 | Hall effect current sensor 625A .69" gap new | Honeywell | CSLA1EL | Mouser | 61 | 0 | 1 | 1 | 2 | 0 | 61 | 61 | 122 |  |  | CSLA1EK 325A .38" gap not stocked
39 | contactor DC 500A 900V 48V coil | Tyco | LEV200 | Thunderstruck Motors | 125 | 1 | 1 | 1 | 3 | 125 | 125 | 125 | 375
40 | fuse 200A 150VDC slow blow | Ferraz Shawmut | A15QS200-4 | Allfuses.com | 27 | 1 | 1 | 1 | 3 | 27 | 27 | 27 | 81
41 | insulated stud 3/8" UNC |  |  | n/a | 0 | 2 | 2 | 2 | 6 | 0 | 0 | 0 | 0 | n/a | yes | leftover from EV conversion project
42 | LiFePO4 cell 100 Ah | HiPower | 100Ah | n/a | 0 | 16 | 11 | 0 | 27 | 0 | 0 | 0 | 0 | n/a | yes | circa 2009, low use
43 | LiFePO4 cell 100 Ah | CALB | CA100 | Thunderstruck Motors | 155 | 0 | 5 | 16 | 21 | 0 | 775 | 2480 | 3255 |  |  | EV West price
44 | THHN/THWN-2 10 ga red insulated wire |  |  | Home Depot
45 | THHN/THWN-2 10 ga black insulated wire |  |  | Home Depot
46 | THHN/THWN-2 6 ga red insulated wire |  |  | Home Depot
47 | THHN/THWN-2 6 ga black insulated wire |  |  | Home Depot
48 | 1/2" galvanized conduit |  |  | Home Depot
49 | 3/4" galvanized conduit |  |  | Home Depot
50 | 1/2" galvanized conduit joints |  |  | Home Depot
51 | 3/4" galvanized conduit joints |  |  | Home Depot
52 | 1/2" galvanized clips |  |  | Home Depot
53 | 3/4" galvanized clips |  |  | Home Depot
54 | 1/2" galvanized weatherproof breakout boxes |  |  | Home Depot
55 | 1/2" galvanized end mounts |  |  | Home Depot
56 | 3/4" galvanized end mounts |  |  | Home Depot
57 | weatherproof grommets for solar panel cables |  |  | TBD
| total | [8 empty] | 6169 | 6115 | 7820 | 20104
| estimated incremental annual savings | [8 empty] | 500 | 500 | 500 | 1500
| ROI, years | [8 empty] | 12.338 | 12.23 | 15.64 | 13.4027
[13 empty] | 17.9 | if no leftover solar panels or batteries being used